# Resource leveling

## Resource Leveling - why

First, a simple question.  Why level resources?  Simply put, if resources are not leveled, resources are either over allocated or under allocated (or both).  Over allocation means the scheduled work is not likely to occur (or the resource may be annoyed, overworked or burned out).  Under allocation means suboptimal utilizing and billing of resource, lowering of profitability.  Lastly, your schedule won’t be accurate, unless resources are correctly loaded.

As a rule, I’ve always used the Dependency Driven approach, where most every task is linked explicitly.  Simply put, the Dependency Driven approach is using dependencies (predecessors) to sequence work to be done by a given resource.  The common myth is that resource leveling never works in the real world, breaks project plans, and should be avoided like the plague.  Much of this myth is due to lack of understanding of how to utilize the tool at hand (our friend, MS-Project).   To start with, the Dependency Driven approach proscribes an overuse of dependencies which masks the actual work-related dependencies.  In all fairness, not every project is a candidate for resource leveling, in fact for resource leveling to be effective, the underlying plan already constructed should already have the following characteristics:

- Minimum number of tasks with more than one resource assigned

- Removal of any constraints that are not absolutely necessary

What’s common wisdom for Resource Leveling?

- Never click automatic resource Leveling

- Always save your plan before even thinking of resource leveling

- It messes up your plan, throwing tasks in random order, and blowing dates

- It’s hopelessly broken and unworkable

Well, let’s explore Resource Leveling and utilization, and you may find my analysis below can help save huge time and effort in using Level Resources to optimize your plans.  Let’s start with how MS-Project reports overutilization.

## Crying wolf: how MS-Project over-reports resource over allocation

Has MS-Project ever identified resources as over allocated while you believe the plan is correct?  Well, the calculation engine in MS-Project is somewhat primitive and can over-report utilization.  As an example, I created a plan with three one hour tasks that occur on the same day.  MS-Project immediately flags me as over allocated, even though I only work three hours in an eight hour day.  That’s because MS-Project schedules all tasks to start at the same time of the day.  Let’s have a look at a simple 3-task plan:

Here’s the resource sheet, note I am “red” meaning overallocated:

Here’s the resource graph:

Why am I over allocated?  Let’s take a closer look at the default resource scheduling by MS-Project by looking at the Resource Usage view, looking in 15 minute increments at how these tasks get scheduled by default:

Clearly, the tasks are all scheduled to start at 8am.

Interestingly, if I use “Level Resource” it will not fix the problem, unless I set a high level of granularity, by telling the leveling engine to fix problems minute-by-minute or hour-by-hour.  Note the default “day-by-day” leveling will not fix the problem.  Here’s how it looks after I level on an hour-by-hour basis:

Note the red is gone, indicating there is no more over allocation.  The actual calculation engine will report over allocation if a resource has to work for more than 60 seconds in any one minute of a project.  This is because the scheduling and calculations is a bit simplistic, combined with MS-Project natively using one-minute increments for calculations.  There are three basic approaches to resolving this:

- Tools/Resource Leveling
You will need to set fine granularity (hour-by-hour in this case) for leveling.

- Edit Task Usage
View/Task Usage and change the minor time scale to hours, then manually edit the working hours so there is no overlap.

- Adjust units
Set the Resource Units of the two tasks to be 50% on both so when there is an overlap the maximum is 100%. Make this edit by selecting Window/Split and change the units in the Task Entry form that appears in the lower window.  The man-hours of work can be edited here as well to more realistic amounts if appropriate.

## Resource Leveling –approaches

There are really three approaches to creating a project plan that has resource appropriately allocated.  Your choice strongly affects the effort you will put into the plan up front, and how much effort needed as you manage the plan.  MS-Project indeed can be frustrating or rewarding, depending on how it is used and how well you understand its behavior.

| Approach | Common use | Pros | Cons |
| --- | --- | --- | --- |
| Enter tasks each with hard-coded dates | This is the intuitive approach taken by people new to MS-Project | Fast, simple, easy, intuitive | Brittle and inflexible Of very limited value Cannot easily adapt to changes, resource scenarios, or actuals that differ from planned. Completion dates are not calculated. No better than using a spreadsheet. |
| Dependency Driven | Every single task is linked in a start to finish chain, even those assigned to a single resource | Intuitive sequencing of resource efforts More flexible | Noisy Gantt Harder to play with resourcing scenarios |
| Traditional WBS | Formal project management approach Build a work breakdown structure (WBS), draw a network diagram, estimate task duration and cost, assign resources, and resource-level the schedule | Enables resource scenarios and resource leveling | Less intuitive |

## How to approach leveling

Prior to leveling (or more likely, to tune the way Level Resources works), you may want to set the task priorities.  Just add a column for “Priority”.  Priority is an indication of a task's importance and availability for leveling. Tasks with the lowest priority are delayed, and those with the highest priority tend to be scheduled earlier.  The priority value that you enter is a subjective value between 1 and 1000, which enables you to specify the amount of control you have over the leveling process. For example, if you don't want Project to level a particular task, set its priority level to 1000. By default, priority values are set at 500.

In most cases, consider leveling over allocated resources only after you have entered all information about task scheduling and resource.  In some cases, you might want to level resources, examine the outcome, and then adjust other task and assignment information.

When entering schedule information for your tasks, keep the following in mind to make sure MS-Project schedules your project accurately, and to help prevent unnecessary resource over allocations.  Here are some tips:

- Task Dependencies
Use task dependencies to reflect a necessary sequence of events. Don’t overuse them, as each additional dependency can result in resource underutilization or completion date slippage.

- Constraints
Avoid inflexible constraints, except where necessary.  
Inflexible constraints are those tying a task to a date. The inflexible constraints are Must Finish On and Must Start On date constraints. You can specify that a task must start on or finish no later than a particular date.  Note such constraints limit the adjustments that Project can make when determining which tasks to adjust when leveling resources.

- Priorities
These values act as “hints” to the resource leveling engine that affect the schedule sequencing of tasks.  Tasks with the lowest priority are delayed or split first. Use a task priority of 1000 (meaning do not level this task) only when a task absolutely cannot be delayed.  500 is the default value.

Some recommendations on settings when leveling resources:

- Never use “Automatic”
Manual is best, so you don’t get blindsided by automatic changes.  Plus automatic changes can be slow in a large plan.

- Start with “Day by Day” for over allocation.  If you need to eliminate all over allocations, go with minute-by-minute.

- Enable “Clear leveling values before leveling”
Otherwise you will accumulate delays and elongate the plan

- Level the entire project or from the current day forward
You may wish to delete leveling for a range of tasks, which you can easily do afterwards.

- Use “Priority, Standard” leveling order
This allows you to use “Priority” as a hint to task sequencing.  See the section below for more information on what is going on in the engine for this setting.

- Enable “Leveling Can Adjust Individual Assignments On A Task” only if you find that resources are insufficiently allocated.  This setting allows multiple resource assigned to a task get their day-to-day assignments tuned to optimize completion of the task.  This setting will have no effect unless multiple resources are assigned to one task.

- Disable “level only within available slack” if you want some meaningful resource leveling, but note this enables the engine to adjust your completion date.

- Disable “Leveling Can Create Splits In Remaining Work” unless you are ok with work getting stopped and started at random to create full utilization.  Bear in mind there are stresses and task switching overhead for human beings that get yanked between tasks seemingly at random.

## What “Leveling Order” does

There are three values for leveling order, which drive how the underlying leveling engine performs.  Here’s what’s going on for each of these values:

| Setting | Meaning |
| --- | --- |
| ID Only | MS-Project will delay tasks with higher Task ID values first before looking at lower IDs. This basically means that tasks listed at the top of the page automatically have a higher priority in the leveling algorithm than tasks at the bottom of the page. |
| Standard | MS-Project examines the following criteria in the order they are listed to determine how to act on over allocated tasks and which to delay first: Predecessor relationships Slack (the number of time units that a task can be delayed without changing the finish date of the project) Dates Priorities Constraints MS-Project will honor predecessor relationships first so that the leveling solution will not have tasks violating their relationships. Then, among tasks that have similar relationships, those tasks with higher slack will be moved before those with lower slack values. Then task dates, priorities, and constraints will be taken into account, in that order. This method is the default and is the one that is most commonly chosen for leveling. |
| Priority Standard | This method takes the same criteria into account as the Standard method, except that it looks at priority first. Using this method, the task priority is the primary driver factor to determine how Project will delay your tasks. With this method, tasks with lower priorities are leveled first, and tasks with the same priority will be delayed based on the other criteria. This method gives you control over how Project will make its leveling decisions. For example, if you have a task that you do not want touched by leveling, you can give it a Priority of 1,000 (values range from 0 to 1,000), which means “Do not level.” With 1,000 priority choices, you have very granular control over the process. |

My recommendation?  Only use “ID Only”, I use a minimum amount of adjustments to “Priority” values, but then use “Priority Standard” so my priority settings then get taken into account.

When MS-Project levels resources, it only delays tasks (or splits tasks if you have allowed that). It does not:

- Reassign tasks
It is up to the PM to make the resource assignments.

- Optimize a resource's allocation
Because leveling does not move tasks earlier or reassign units, a resource flagged as over allocated might become under allocated as a result of leveling.  If you have multiple resources assigned to each task at varying units, you are likely to have under allocated resources, as MS-Project will level to ensure there is no over allocation.

- Reassign units 
For example, if I am assigned to work on two tasks that are both scheduled at the same time, leveling won't change my units so that I work on both tasks at 50 percent.

When you're ready to have Project level resources, on the Tools menu, click Level Resources. To accept all the defaults, click Level Now.

After Project finishes leveling an over allocated resource, certain tasks assigned to that resource are split or delayed. The split or delayed tasks are then scheduled for when the resource has time to work on them. You can see the results of leveling in the Leveling Gantt view, which graphically shows pre-leveled values compared with post leveled values, including newly added task delays and splits.

## The effect of delay on leveling and scheduling

Leveling delay lets a project manager precisely manage the start and end of every task without adding dependencies and without fixing the start date. Leveling delay is a hidden field that exists at two places: the task level and the resource-assignment level:

- Task Level
Task level is the easiest to apply, but the hardest to manage. Simply add the “Leveling Delay” column to the Gantt chart view, or use the “Leveling Gantt” view. Enter the number of hours or days delay, and the entire task shifts out in time. Note the delay must be in elapsed days or hours. Elapsed days do not honor holidays and non-work time. A project manager must often adjust these delays manually as task start and end dates shift.

- Resource Level
Resource-assignment leveling delay can be entered for each resource assigned to a task. It can be entered in work-hours or work-days. It provides flexibility to level out any imaginable work. If two people are assigned to a task, but only one is over allocated by 4 hrs, delay the over allocated resource by 4 hrs. The other resource’s start date is unaffected. To delay the entire task, though, every resource assigned to the task must be delayed. Make maintenance simpler; allocate one and only one resource per task.

Leveling delay is measured from the dependencies of the task. For instance, if task #4 and task #5 are both dependent upon task #3, ending on Monday, they will both begin on Tuesday with no delay. Putting a two-day delay on #5 will make task #4 starts on Tuesday and #5 starts on Thursday. If the end-date of #3 moves to Tuesday, they will both roll forward to Wednesday and Friday start-dates.

By combining units (% allocation) and leveling delays, a project manager can accurately represent complex work. People can work multiple tasks simultaneously; participate in multiple chains of dependent tasks, and still work all available work hours, and not one hour more.

“Level Resources” adds a “Leveling Delay” that is visible as a column (field) in MS-Project.  This is shown in Elapsed Days (edays) that represent calendar (elapsed) time, and not work time.  You can use the short hand “ed” (such as 5ed) to represent 5 elapsed days, and you can edit these fields, either to manually remove or adjust the output of leveling resources.

Some observations looking at the Leveling Gantt view, looking at “Leveling Delay”:

- Task ID 2 and 3 were slipped within the same day to avoid over allocation

- Task ID 7 has a predecessor Task ID 4, so the later has no green trailing line

- Since priority was not set, the tasks are generally in ID order

Task level delays described above move an entire task with all assignments.  A more fine-grained adjustment is to insert delays at the resource (assignment) level within a task.

In summary, Level Resources requires some understanding to use effectively, but it can save you significant effort in tuning a plan to effectively utilize resources to achieve your project objectives.

About the author: Joel Plaut has functioned as head of PMO, as well as CIO and CTO of public companies. With 23 years of experience as a leader in financial services, insurance and financial publishing, Joel brings a great deal of knowledge and expertise in strategy and execution managing, designing, developing and deploying enterprise-class systems.

Copyright © 2009 Technology Management (TM). All Rights Reserved.